## Instructions
TEAM NAME	Ssad 45
PROJECT NAME	generating pdf
PROJECT MENTOR	sane sushmitha reddy
TEAM MEMBERS	veerendra mandava
	ayush joshi
	prakhar pandey

## Team_Status
TEAM NAME	Ssad 45
PROJECT NAME	generating pdf
PROJECT MENTOR	sane sushmitha reddy

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 5 (August 31- sept 6)
getting familiar with Django and making demo app	Preparation	ayush	13-15 hours	14 hours	Done	we had learnt from official documentation.	#VALUE!	#VALUE!
getting familiar with report lab	Preparation	veerendra	8 to 10 hours	11 hours	Done	we had learnt from official documentation.	#VALUE!	#VALUE!
team meeting	Coordination	prakhar	45 min	1 hour	Done
status tracker	Documentation	ayush	30 min	20 min	Ongoing
role preferences	Preparation	prakhar	30 min	30 min	Done
client meetings	Coordination	veerendra	10 min	15 min	Done
Week 6 (sept 7- sept 13)
team meeting	Coordination	prakhar	45 min	1 hour	Done
status tracker	Documentation	ayush	30 min	20 min	Ongoing
client meetings	Coordination	veerendra	10 min	15 min	Done
generating a basic pdf	Design	prakhar	5 to 6 hours	5 hours	Done
integrating django and report lab	Development	veerendra	8 to 9 hours	9 hours	Done		#VALUE!	#VALUE!

Week 9(sept 20-sept 26)
creating pie charts	Development	veerendra	8 to 9hours	6 hours	Done		#VALUE!	#VALUE!
test plan document	Documentation	ayush	45 min	30 min	Ongoing
intergrating pie chart in django	Development	prakhar	4-5 hours	3 hours	Done
status tracker	Documentation	ayush	45 min	30 min	Done		#VALUE!	#VALUE!
Week 10(sept29- oct 6)
adjusting table sizes	Development	veerendra	2-3 hours	3 hours	Done		#VALUE!	#VALUE!
Learning about Javascript in reportlab	Preparation	prakhar	1-2 hours	1.5 hours	Done
status tracker	Documentation	ayush	20 min	20 min	Done		#VALUE!	#VALUE!
presentation of R1	Documentation	ayush	2-3 hours		Ongoing
team meeting	Coordination	prakhar	15 min	15 min	Done		#VALUE!	#VALUE!
Learning about Codeplay in reportlab	Development	veerendra	1-2 hours	1.5 hours	Done		#VALUE!	#VALUE!
Week 12(oct8-Oct14)
implementing javascript in reportlab	Development	veerendra	2-3 hours	2 hours	Ongoing		#VALUE!	#VALUE!
status tracker	Documentation	ayush	20 min	20 min	Done		#VALUE!	#VALUE!
team meeting	Coordination	prakhar	1 hour	1 hour	Done		#VALUE!	#VALUE!

Week 15(Nov1-8Nov)
implementing video in pdf	Development	veerendra	2-3 hours	2 hours	Done		#VALUE!	#VALUE!
client meetings	Coordination	prakhar	20 min	20 min	Done		#VALUE!	#VALUE!
status tracker	Documentation	ayush	20 min	20 min	Done		#VALUE!	#VALUE!
team meeting	Coordination	ayush	20 min	20 min	Done		#VALUE!	#VALUE!
fixing problems on inserting video in pdf	Development	veerendra	2-3 hours	2 hours	Done
Design Document	Development	prakhar	1 hour	1 hour	Done
Week 14

Week 15

Week 16

Week 17

## Individual_Status
TEAM NAME	45
PROJECT NAME	generating pdf
PROJECT MENTOR	sane sushmita reddy

Actvities	veerendra mandava		ayush joshi		prakhar pandey		0		0		Estimated Total Hours	Actual Total Hours
	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent
Week 5 (August 31- sept 6)
getting familiar with Django and making demo app	10-11 hours	9 hours	10-11 hours	10 hours	10-11 hours	11 hours	0	0	0	0	#VALUE!	#VALUE!
getting familiar with report lab	7-8 hours	8 hours	7-8 hours	7 hours	7-8 hours	6 hours	0	0	0	0	#VALUE!	#VALUE!
role preferences	30 min	30 min	30 min	30 min	30 min	30 min
team meetings	1 hour	1 hour	1 hour	1 hour	1 hour	1 hour
client meeting	15 min	15 min	15 min	15 min	15 min	15 min
status tracker	20 min	20 min	20 min	20 min	20 min	20 min
Week 6 (sept 7- sept 13)
integrating django and report lab	8-9 hours	7 hours	8-9 hours	9 hours	8-9 hours	8 hours	0	0	0	0	#VALUE!	#VALUE!
team meetings	1 hour	1 hour	1 hour	1 hour	1 hour	1 hour
client meeting	15 min	15 min	15 min	15 min	15 min	15 min
status tracker	20 min	20 min	20 min	20 min	20 min	20 min
generating a basic pdf	5-6 hours	6 hours	5-6 hours	5 hours	5-6 hours	6 hours
0
Week 9(sept 20-sept 26)						0	0
						0	0
0						0	0
Week 9(sept 20-sept 26)						0	0
creating pie charts	5-6 hours	6 hours	5-6 hours	5 hours	5-6 hours	4 hours					#VALUE!	#VALUE!
test plan	45 min	30 min	45 min	30 min	45 min	30 min
integrating django and pie charts	5-6 hours	4 hours	5-6 hours	5 hours	5-6 hours	6 hours
status tracker	45 min	20 min	45 min	20 min	45 min	20 min					#VALUE!	#VALUE!
						0	0
Week 10(sept29-oct 6)						0	0
adjusting table size	2-3 hours	2 hours	2-3 hours	2.5 hours	2-3 hours	2 hours					#VALUE!	#VALUE!
status tracker	20 min	20 min	20 min	20 min	20 min	20 min					#VALUE!	#VALUE!
Learning about Javascript in reportlab	2-3 hours	1 hour	2-3 hours	1.5 hour	2-3 hours	1 hour					#VALUE!	#VALUE!
Learning about Codeplay in reportlab	1-2 hour	1 hour	1-2 hour	1 hour	1-2 hour	1 hour					#VALUE!	#VALUE!
R1 presentation	1-2 hour	1.5 hour	1-2 hour	1.5 hour	1-2 hour	1.5 hour					#VALUE!	#VALUE!
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
Week 15(Nov1-8Nov)						0	0
implementing video in pdf	2-3 hours	2 hours	2-3 hours	2.5 hours	2-3 hours	2 hours					#VALUE!	#VALUE!
client meetings	20 min	20 min	20 min	20 min	20 min	20 min					#VALUE!	#VALUE!
Design Document	1 hour	1 hour	1 hour	1 hour	1 hour	1 hour					#VALUE!	#VALUE!
fixing bugs on insertion of video	2-3 hours	2 hours	2-3 hours	1.5 hour	2-3 hours	2.5 hours
status tracker	20 min	20 min	20 min	20 min	20 min	20 min					#VALUE!	#VALUE!
Week 14						0	0
0						0	0
0						0	0
0						0	0
0						0	0
Week 15						0	0
0						0	0
0						0	0
0						0	0
Week 16						0	0
0						0	0
0						0	0
0						0	0
0						0	0
Week 17						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0